## Sheet1
Final Project for Portfolio 2 - Water Physics Based Off of Metaballs
Daniel Schenker
Typical Week | Total Hours | Occurences | Duration
Notes: | All times include transportation time
Sleeping | 70 | 7 | 10
School | 25 | 5 | 5
Homework | 20 | 5 | 4
Eating | 14 | 28 | 0.5
Gym | 6 | 2 | 3
Church | 5 | 1 | 5
Grocery Shopping | 4 | 2 | 2
Cleaning & Dishes | 4 | 8 | 0.5
Other | 3.5 | 7 | 0.5
Laundry | 2.5 | 1 | 2.5
Bible Reading | 2.31 | 7 | 0.33
Total Available | 168 | 7 | 24
Total Used | 154 | 7 | 22
Time Leftover | 11.69 | 7 | 1.67
Months | Total Days | Work Days | Work Hours | Reasoning
September | 30 | 0 | 0 | The first week I am preparing for final exams. The second week I have final exams. The third and fourth weeks I am away on holidays.
October | 31 | 27 | 45.09 | First month of my third last semester, probably will have more free time as a result. Last four days are preparation for midterm exams.
November | 30 | 21 | 35.07 | First four days are preparation for midterm exams. The second week I have midterm exams. The rest of the month I only have normal classes.
December | 31 | 1 | 1.67 | The first day I am free. The second week I am preparing for final exams. The third week I have final exams. The rest of the month I am on holidays.
January | 31 | 26 | 43.42 | First month of my second last semester, probably will have more free time as a result. The last five days are preparation for midterm exams.
February | 28 | 20 | 33.4 | The first three days are preparation for midterm exams. The next five days I have midterm exams. The rest of the month I only have normal classes.
March | 31 | 16 | 26.72 | The first two days I am free. The second week I am preparing for final exams. The third week I have final exams. The last two weeks I have holidays, but plan to work on this project for the duration of them.
April | 30 | 27 | 45.09 | First month of the last semester. The whole month I only have normal classes, except for the last three days, in which I am preparing for midterm exams.
May | 31 | 21 | 35.07 | The first four days I am preparing for midterm exams. The second week I have midterm exams. The rest of the month I only have normal classes.
June | 15 | 1 | 1.67 | The first day I am free. The second week I am preparing for final exams. The third week I have final exams. The rest of the month I am on holidays.
Total (9.5) | 288 | 160 | 267.2
Percentage of days that are work days: |  |  | 55.5556
Course suggested 30 hour work weeks: |  |  | 9
Planned 30 hour work weeks: |  |  | 8.9067
Projected Completion Date | Milestones
2D
Research
2012-09-27 |  |  | Determine what engine I would like to use
2012-10-06 |  |  | Learn how the engine I've decided to use works, and figure out the limitations and maximum potential of the engine I've chosen
Overall Architecture
2012-10-14 |  |  | Lay out the overall architecture for the project itself
Rendering
2012-10-31 |  |  | Render a single metaball on the screen without motion or animation based purely off of data (not by loading a pre-existing image)
2012-11-15 |  |  | Render a single metaball on the screen with motion and animation based purely off of data (not by loading a pre-existing image)
Input
2012-11-30 |  |  | Incorporate input according to my metaball ideas.txt
Collision
2013-01-04 |  |  | Add collision detection between metaballs and the outside boundary that highlight metaballs a certain colour upon collison, but simply get teleported back to the center of the room upon collison, while maintaining their previous statistics prior to collision detection
2012-01-17 |  |  | Add collision physics to metaballs that have collided with the outside boundary
2012-01-30 |  |  | Add collision detection between metaballs that highlights the metaballs that are in contact a different colour, but doesn't actually act upon the collision
2013-03-02 |  |  | Add collision physics to metaballs that have collided with other metaballs
Gravity
2013-03-20 |  |  | Add gravity at a constant acceleration
2013-03-22 |  |  | Add a toggle that can be used to control whether gravity is on or off run time
2013-03-24 |  |  | Add a slider that can be used to control the strength of gravity run time
User Controllable Objects
2013-04-07 |  |  | Add objects that can be controlled by the user, that are used to interact with the environment
Fine Tuning
2013-04-23 |  |  | Make the game fun
Front End
2013-04-27 |  |  | Implement menus
3D
2013-05-29 |  |  | I would like to convert this project to 3D eventually, but this is more of an optional goal based on time and difficulty. As I do not know how difficult this project is yet, as I am not taking calculus till next semester, I will have to decide later on. For now however, I will keep my focus to 2D, just in case 3D is too ambitious, as it is always easier to add work rather than to cut back.
Final Touches
2013-06-10 |  |  | Ensuring that everything is worthy of final product material
Potential engines to use |  | Comments
OpenGL |  | I would like to use openGL as I will mostly be using DirectX in school, and it would be good to be able to use both of the industry's leading standards. Also I would like to work for Nintendo or Sony, and DirectX does not work on those consoles, thus adding to the reason to choosing openGL
Simple Game Engine by Peter Chan |  | The first game engine that I have ever used that displayed graphics using C++ was this engine, so my familiarity with it would help speed the process of getting this project going
2D Boy |  | I do not know much about 2D Boy yet, but I would like to research this further as my teacher Malcolm Stead recommended it as a possible engine to use. I also like the physics in the game World of Goo, which was made by 2D Boy
DirectX |  | This will be the engine I use the most in school, so it only makes sense that this would be the simplest option, but I am considering other engines first as I would like my primary focus to be the physics, with my secondary focus to be the graphics
Additional Comments
I know that I tend to overwork, trying to do more than the minimum. This is why my planned schedule is not as busy as it can be
Also times are tentative, as I am going to be taking my first calculus course next semester, and I have done very little graphical programming before, so once I have a better understanding of the difficulty and time required in order to complete a task, I will update this schedule